## Sprint-1
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 5 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-09-18 | 2022-09-20 | 2022-09-22 | 2022-09-24 | 2022-09-26 | 2022-09-28 | 2022-09-30
16
| Selecting on the technology stack | All | 6 | 0 | 2 | 2 | 2
| Research on additional libraries and frameworks to be used | All | 6 | 0 | 2 |  | 2 |  | 2
| Identifying the hosting environment | All | 4 | 0 |  |  |  | 1 | 1 | 2
|  | Total | 16 | 16 | 12 | 10 | 6 | 5 | 2 | 0
|  | Ideal | 20 | 20 | 17 | 14 | 11 | 8 | 4 | 0
Team:
Chirag Arora | 4 hours / Week
Sai Prashanth Guthula | 4 hours / Week
Santosh Sai Gowtham Pasala | 4 hours / Week
Lokesh Reddy Gangasani | 4 hours / Week
Total Available Hours During Sprint: | 16

## Sprint-2
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 5 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-02 | 2022-10-04 | 2022-10-06 | 2022-10-08 | 2022-10-10 | 2022-10-12 | 2022-10-14
20
| Building few UI wireframes | Chirag Arora | 5 | 2 |  | 2 |  |  | 1
| Identifying possible schemas for DB | Lokesh Reddy Gangasani | 5 |  | 2 |  |  | 2 | 1
| Setting up backend project structure | Sai Prashanth Guthula | 5 |  |  | 2 | 1 |  |  | 2
| Setting up frontend project structure | Santosh Sai Gowtham Pasala | 5 |  |  |  | 2 |  | 1 | 2
|  | Total | 20 | 18 | 16 | 12 | 9 | 7 | 4 | 0
Team: |  | Ideal | 20 | 20 | 17 | 14 | 11 | 8 | 4 | 0
Chirag Arora | 5 hours / Week
Sai Prashanth Guthula | 5 hours / Week
Santosh Sai Gowtham Pasala | 5 hours / Week
Lokesh Reddy Gangasani | 5 hours / Week
Total Available Hours During Sprint: | 20

## Sprint-3
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 5 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-16 | 2022-10-18 | 2022-10-20 | 2022-10-22 | 2022-10-24 | 2022-10-26 | 2022-10-28
20
| Build the remaining wireframes | Chirag Arora | 2 |  | 2
| Database Created & Updated DB Design | Sai Prashanth Guthula | 5 | 2 |  |  |  | 2 |  | 1
| Architecture diagram | Lokesh Reddy Gangasani | 5 |  |  | 2 | 2 | 1
| Identified number of components needs to be developed | Santosh Sai Gowtham Pasala | 5 |  | 2 |  | 1 |  | 2
| Identified number of API's needs to be created | Chirag Arora | 3 |  | 3
|  | Total | 20 | 18 | 11 | 9 | 6 | 3 | 1 | 0
|  | Ideal | 20 | 20 | 17 | 14 | 11 | 8 | 4 | 0
Team:
Chirag Arora | 5 hours / Week
Sai Prashanth Guthula | 5 hours / Week
Santosh Sai Gowtham Pasala | 5 hours / Week
Lokesh Reddy Gangasani | 5 hours / Week
Total Available Hours During Sprint: | 20

## Sprint-4
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 5 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-10-30 | 2022-11-01 | 2022-11-03 | 2022-11-05 | 2022-11-07 | 2022-11-09 | 2022-11-11
20
Integrating API to it's component | Implement a Random Gate assignment | Santosh Sai Gowtham Pasala | 5 | 2 |  |  | 1 |  | 2
| Create Airport profile | Chirag Arora | 3 |  |  | 1 |  |  |  | 2
| Airport Employee dashboard | Sai Prashanth Guthula | 5 |  | 2 |  | 2 |  | 1
| Airline Employee dashboard | Chirag Arora | 2 | 1 |  |  |  | 1
| Create mongo database | Lokesh Reddy Gangasani | 5 |  | 2 |  | 1 | 1 |  | 1
|  | Total | 20 | 17 | 13 | 12 | 8 | 6 | 3 | 0
|  | Ideal | 20 | 20 | 17 | 14 | 11 | 8 | 4 | 0
Team:
Chirag Arora | 5 hours / Week
Sai Prashanth Guthula | 5 hours / Week
Santosh Sai Gowtham Pasala | 5 hours / Week
Lokesh Reddy Gangasani | 5 hours / Week
Total Available Hours During Sprint: | 20

## Sprint-5
Backlog Item | Task | Task Owner | Initial Estimate (Total Sprint Hours = 5 x4) | D1 | D2 | D3 | D4 | D5 | D6 | D7
|  |  |  | 2022-11-13 | 2022-11-15 | 2022-11-17 | 2022-11-19 | 2022-11-21 | 2022-11-23 | 2022-11-27
20
| Integrate frontend and backend for login signup | Sai Prashanth Guthula | 3 | 2 |  | 1
| integrated db with Airline profile | Lokesh Reddy Gangasani | 3 | 1 | 2
| integrated backend with frontend for userprofile | Santosh Sai Gowtham Pasala | 3 |  |  | 2 | 1
| integrate all components | Lokesh Reddy Gangasani, Santosh Sai Gowtham Pasala | 6 |  | 2 | 1 | 2 | 1
| Create AWS instance and load balancer, autoscaling | Chirag Arora | 3 |  | 2 |  |  | 1
| Deployment | Sai Prashanth Guthula,Chirag Arora | 6 |  |  |  |  | 2 | 2 | 2
|  | Total | 24 | 21 | 15 | 11 | 8 | 4 | 2 | 0
|  | Ideal | 24 | 24 | 20 | 15 | 10 | 5 | 3 | 0
Team: | 6 hours / Week
Chirag Arora | 6 hours / Week
Sai Prashanth Guthula | 6 hours / Week
Santosh Sai Gowtham Pasala | 6 hours / Week
Lokesh Reddy Gangasani | 24
Total Available Hours During Sprint: